## Sheet1
0
CPDandS Work Plan 2025/2026
Governance
Q1 | Ensure agenda covers quarterly review of workplan & update on progress at each meeting. | LPC Self-Assessment collated and circulated post review at March 2025 LPC meeting | Annual review of members' governance documents before being confirming they are available for review on LPC website. | Collate completed skills matrix forms from committee members and employees and identify next steps in partnership with the LPC exec team | Produce and share action plan for LPC and sub committees on any areas needing strengthening as identified during the completion of the LPC Self-Asessment | Review CPNEC website to check following are available to view - Note on how to access declaration of interests for committe members Constitution • Governance Framework • Committee member role descriptions • Confidentiality Policy • Conflicts of interest • Bribery Act • Competition Law Compliance • Corporate Governance | Q1 - Quarterly Governance sub-committee to meet and progress actions
Q2 | Ensure agenda covers quarterly review of workplan & update on progress at each meeting. | Review written evidence submitted by sub-committees and employees of the LPC for evidence towards the LPC Self-Assessment | Governance sub-committee to develop a checklist on what is required at each meeting to meet LPC Self-Assessment standards | Review development opportunities for committee members and LPC employees to enhance contractor support. | All sub-committees to provide documented evidence for LPC Self-Assessment as requested in the action plan shared by the governance sub-committee | Q2 - Quarterly Governance sub-committee to meet and progress actions
Q3 | Ensure agenda covers quarterly review of workplan & update on progress at each meeting. | Agenda item on LPC meeting to review progress in LPC Self-Assessment | Interrogate any decisions made regarding contract applications in previous six months and confirm they were dealt with appropriately. | Ensure an appropriate skill and expertise mix of members in order to conduct committee business | Governance sub-committee to use checklist developed in Q2 at each meeting and feedback at end of each meeting on status. | Q3 - Quarterly Governance sub-committee to meet and progress actions
Q4 | Ensure agenda covers quarterly review of workplan & update on progress at each meeting. | Review if skills matrix completion exercise needs to be re-completed for all LPC members | Annual review of members' governance documents before updating on LPC website with any changes . | Ensure an appropriate skill and expertise mix of members in order to conduct committee business. | Annual review of exisiting LPC policies. Update as appropriate. (Whistle-blowing policy, Expenses policy, Social Media policy, Complaints policy, Privacy policy and any others as identified by CPE or LPC as required) | Light touch completion of LPC Self-Assessment in readiness for new financial year for LPC | Q4 - Quarterly Governance sub-committee to meet and progress actions
Finance
Q1 | Q1 - Quarterly Governance sub-committee to meet and progress actions | Share verbal update of current financial status at Committee meeting
Q2 | Q2 - Quarterly Governance sub-committee to meet and progress actions | Share written report of current financial status at Committee meeting
Q3 | Q3- Quarterly Governance sub-committee to meet and progress actions | Share verbal update of current financial status at Committee meeting
Q4 | Q4 - Quarterly Governance sub-committee to meet and progress actions | Share written report of current financial status at Committee meeting
Services
Q1 | Grow national and local service delivery | Encourage pharmacies to provide commisioned services. | Provide training on hypertension case finding service and use of ABPMs | Subgroup meeting every two months | Use of pharmacy services coach to engage with GP practices and encourage Pharmacy First referrals
Q2 | Commission or source two local training events to suuport new services | Meeting with NHSBSA and NPA to maximise income, including private services supported by NPA sponsors and Edinpharm | Provide DMS and NMS training at AGM, concentrating on antidepressants for the new NMS regulations | Use Pharmacy services coach to engage with pharmacies with low activity , provide average income potential per service to highlight income streams being missed. Fees, Time taken, skills required, produce quick reference guide per service (This is a quick reference regarding income missed vs dispensing rather than a how to guide for the service , CONTRAST against income from dispensing.
Q3 | Review of all local service fee structures | Pull together list of services in Sunderland and Durham and create table of fee structures. Traffic light services against other areas. Underpaid Red - Market Rate Amber - Aspirational above market rate Green. Ann working on this. | Use of pharmacy services coach to engage with GP practices and encourage Pharmacy First referrals. Hopefully TPP referral button will increase engagement of Systm1 practices
Q4 | Continue use of pharmacy services coach to engage with GP practices and encourage Pharmacy First referrals.
Communications and Engagement
Q1 | Produce ID cards/lanyards for officers/members. | Write again to MPs. Commission space within the Durham/Sunderland edition of raring2go to market PF. Source the dates of Sunderland and Durham HWBB meetings. | New web address for LPC website and, using the same domain, establish LPC email addresses for officers, to include a generic email address which can be accessed by more than one officer. | Review website content.
Q2 | Establish the WhatsApp group. Produce ID cards/lanyards for PCN leads. | Via consultation with DCC and SCC promote PF in the schools within the CPDandS footprint. | Review website content. | Review website content.
Q3 | Arrange MP and councillor visits in each of the constituencies. Source examples of positive PF case studies. | At the AGM Include a contractor event to cover BP case finding and Pharmacy contraceptive services. Also anti depressant inclusion in NMS | Review website content. | Hold subgroup meeting
Q4 | Arrange a contractor event | Review website content. Review number and use of new CPDandS.org.uk email addresses | Hold subgroup meeting