## Comms
#VALUE!
Comms Work Plan 2026/2027 | [7 empty] | c
Communications and Engagement
Q1 | Initiate discussions with Sunderland and Durham universities about collaborating on marketing of CP services. Comms and services groups to collaborate on themes. | Source costings for buying digital thermometers and BP machines (large and small cuffs) for all CPDandS pharmacies. | Source details of all Durham and Sunderland councillors. Seek EoI from pharmacies to host visits | Draft a script for use on Cllr pharmacy visits (liaise with CPE comms team) | Confirm with CPE/ICB that their comms resources can be used by LPC/Universities on comms campaign | Hold sub group meeting | Arrange and host contractor event around new contract. CPE hosted a webinar on 1 June. Also, visited Durham on 3 June
Q2 | Engage with comms teams at universities to develop the campaigns and set out a timetable for rollout | Take costings of purchase of digital ear thermometers and BP machines to July CPDandS meeting for discussion and decision. Subject to the outcome of those discussions, arrange purchase and distribution | Arrange and host cllr visits in as many areas/wards as possible. | Hold sub group meeting - 21 July | Review website content | Attend HWBBs as observers. Attended Sunderland HWBB in June | Brand stakeholder list and laminate. Disseminate a copy to all pharmacies, for internal use only
Q3 | Begin rollout of marketing campaigns at the Universities | Attend HWBBs as observers | Arrange and host cllr visits in as many areas/wards as possible. | Hold sub group meeting in late October/early November | Review website content | Review distribution lists, email and mailchimp. Do they include all CPDandS pharmacies? | Brand stakeholder list and laminate. Disseminate a copy to all pharmacies, for internal use only
Q4 | Maintain dialogue with Universities. Discuss success, or otherwise, of collaboration and campaigns. | Attend HWBBs as observers | Review website content | Hold sub group meeting

## Governance
#VALUE!
CPDandS Work Plan 2026/2027
Governance
Q1 | Ensure agenda covers quarterly review of workplan & update on progress at each meeting. | LPC Self-Assessment reviewd by governance group and shared with committee at July 2026 LPC meeting | Annual review of members' governance documents before confirming they are available for review on LPC website. Governance sub-committee to review governace checklist to ensure committee is on track with requirements | Skills matrix forms to be completed for new committee members and employees and identify next steps in partnership with the LPC exec team | Produce and share action plan for LPC and sub committees on any areas needing strengthening as identified during the completion of the LPC Self-Asessment | Review CPNEC website to check following are available to view and within review date - Note on how to access declaration of interests for committe members Constitution • Governance Framework • Committee member role descriptions • Confidentiality Policy • Conflicts of interest • Bribery Act • Competition Law Compliance • Corporate Governance | Q1 - Quarterly Governance sub-committee to meet and progress actions
Q2 | Ensure agenda covers quarterly review of workplan & update on progress at each meeting. | Review work plans submitted by sub-committees and employees of the LPC for evidence towards the LPC Self-Assessment | Governance sub-committee to review governace checklist to ensure committee is on track with requiremnts | Review development opportunities for new committee members and LPC employees to enhance contractor support. | Q2 - Quarterly Governance sub-committee to meet and progress actions | LPC identfied social media as a skills gap. Explore training options.
Q3 | Ensure agenda covers quarterly review of workplan & update on progress at each meeting. | Agenda item on LPC meeting to review progress in LPC Self-Assessment | Ensure an appropriate skill and expertise mix of members in order to conduct committee business | Governance sub-committee to review governace checklist to ensure committee is on track with requiremnts | Q3 - Quarterly Governance sub-committee to meet and progress actions | Ensure social media training has been completed by relevant members
Q4 | Ensure agenda covers quarterly review of workplan & update on progress at each meeting. | Review if skills matrix completion exercise needs to be re-completed for all LPC members | Annual review of exisiting LPC policies. Update as appropriate. (Whistle-blowing policy, Expenses policy, Social Media policy, Complaints policy, Privacy policy and any others as identified by CPE or LPC as required) - reviewed Q1 2026/27, to be reviewed again Q1 2027/28 in line with self assessment | Annual review of exisiting LPC policies. Update as appropriate. (Whistle-blowing policy, Expenses policy, Social Media policy, Complaints policy, Privacy policy and any others as identified by CPE or LPC as required) - reviewed Q1 2026/27, to be reviewed again Q1 2027/28 in line with self assessment | Light touch completion of LPC Self-Assessment in readiness for new financial year for LPC - completed on a monthly basis | Q4 - Quarterly Governance sub-committee to meet and progress actions

## Services
Services
Q1 | Grow national and local service delivery | Encourage pharmacies to provide commisioned services. | Introduce contractors to the 'Your services' tool | Subgroup meeting every two months | Use of pharmacy services coach to engage with GP practices where supported requested and to engage with pharmacies where not engaged with services, such as TPF
Q2 | Commission or source two local training events to suuport new services | Support training to launch the Sunderland Depo contraception service | Support training to launch the Durham STI service | Use BSA services data to identify high and low performing pharmacies to learn and share learning to support service delivery. Pharmacy services coach to engage with pharmacies with low activity. | Commission vaccination training offer for pharmacies
Q3 | Develop PCN leads to morph into becoming neighbourhood leads so there is capacity to engage with neighbourhood meetings when more activity begins | Develop training session dependent upon the outcome of CPCF negotiations | Pharmacy services coach to continue engagement with practices and pharmacies as judged appropriate
Q4 | Pharmacy services coach to continue engagement with practices and pharmacies as judged appropriate | Ensure Depo and STI services well established and running smoothly. If six months' data available, produce business case for commissioning Depo in Durham and STI service in Sunderland | Consider topics for new service commissioning

## Finance_26_27
Finance 26_27
Q1 | Quarterly Governance sub-committee to meet and progress actions | Share verbal update of current financial status at Committee meeting
Q2 | Quarterly Governance sub-committee to meet and progress actions | Share verbal update of current financial status at Committee meeting
Q3 | Quarterly Governance sub-committee to meet and progress actions | Share verbal update of current financial status at Committee meeting
Q4 | Quarterly Governance sub-committee to meet and progress actions | Share verbal update of current financial status at Committee meeting